## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Saumya Singh Rathore | 2024-12-17 | Error with extraction via API | S2 | Saumya Singh Rathore | Compliance | Adhered to the bank policy and extraction documents | 2024-12-20 | Open | Require further investigation
2 | Saumya Singh Rathore | 2025-01-05 | Error with OCR text extraction accuracy | S3 | Saumya Singh Rathore | Bug | Adopted Pre-processing techniques | 2025-01-13 | Closed | Enhanced the accuracy
3 | Saumya Singh Rathore | 2025-01-16 | Error with llm model fine-tuning | S6 | Saumya Singh Rathore | Bug | Utilized distiled versions for better performance | 2025-01-20 | Closed | Improved performance